1	Executive Summary	2

2	RISK MANAGEMENT PROCESS	3

3	RISK REVIEW SCHEDULE	5

4	RISK TRACKING and CONTROL	5

5	APPENDIX A -Taxonomy of potential risks	6

6	APPENDIX B - Risk TRACKING  worksheet	8

7	APPENDIX C - RISK MANAGEMENT WORKSHEET	9

8	APPENDIX d - RISK ACTION STATUS REPORT	29

# Executive Summary

The State of Washington’s Employment Security Department (ESD) in collaboration with the Executive Policy Council (EPC) and the Washington WorkSource Regional Partnerships will implement the Services, Knowledge, and Information Exchange System (SKIES).  This includes:

- Develop modification requirement and specifications

- Develop data conversion and interface specifications and applications

- Design the network

- Tailor the application to support Washington's employment and training business operations

- Install production computer services

- Design new business processes

- Conduct alpha and beta test

- Conduct State-wide implementation

The Project's Management Team has recognized the need to take a proactive approach in the management of risks related to the SKIES Implementation Project.  Consequently, the management of risks for this project will follow a continuous risk management model.

The involvement of the business, technical, executive, and interface partners is crucial to having a viable risk management process.  The approach we will follow will ensure that those aspects are appropriately represented in the project.

Tasks identified for the mitigation of risks will be included in the schedule, as appropriate.  This will ensure that tracking of progress, or lack thereof, occurs and necessary resources are identified.

# RISK MANAGEMENT PROCESS

The SKIES Implementation Project will follow a continuous risk management model.  The model consists of 5 phases.  The phases are Identify, Analyze, Plan, Track and Control.  Each phase has detailed tasks as shown in the following table.

| Phase | Tasks |
| --- | --- |
| Identify | Identify potential risks |
|  | Establish risk categories |
| Analyze | Establish probability and impact definitions |
|  | Evaluate impact of risks |
|  | Evaluation probability of risks |
|  | Rank risks - calculate the exposure |
| Plan | Select risks to be mitigated |
|  | Select mitigation strategies |
|  | Evaluate costs/benefits of mitigation |
|  | Create tracking and control plan |
| Track | Track and report status |
| Control | Take corrective actions |
|  | Adjust control plan as required |
|  | Close risks |
|  | Document lessons learned |

This process allows the project team to develop the initial risk management plan.  Additionally, the risk management plan will be reviewed on a periodic basis as described in the Risk Review Schedule section.

Risk Management Tools

In the Identify phase, a generic list of potential risks is used to stimulate the identification of specific Project risks (see Appendix A).  Once the initial risks are identified, we will categorize them.  The categorized risks will be captured in a Risk Management Worksheet shown in Appendix B.

During the Analyze phase, a Risk Management Worksheet is used to associate definitions, and to quantify the risk impact, probability and exposure.  Mitigation strategies are developed for major risks.

The mitigation strategies are captured on the Risk Management Worksheet. Also identified in this phase are the costs necessary for the implementation of the mitigation strategy.  These costs will be added to the project budget as contingency funds.

In the Track and Control phase, we will use the Risk Action Status Report, which is generated from the Risk Management Worksheet.

The tools to facilitate the risk management process will consist of:

- a taxonomy for identifying the potential risks (see Appendix A),

- a risk management worksheet (see Appendix B) for capturing the risks,

- a risk planning worksheet for evaluating and developing mitigation plans (see Appendix C),

- a risk action status report that will be a part of the project's regular status reporting process (see Appendix D),

- including the mitigation actions and contingency triggers in the project's work plan,

- a quantification matrix for determining risk exposure and ranking the risks.

Impact

| Hi (3) | 3 | 6 | 9 |
| --- | --- | --- | --- |
| Med (2) | 2 | 4 | 6 |
| Lo (1) | 1 | 2 | 3 |
|  | Lo (1) | Med (2) | Hi (3) |

Probability of Occurrence Definitions

#### Impact:

Low - minimal disruption to project progress

Medium - moderate disruption to project progress, schedule implications

High - extended disruption to project progress, cost implications

#### Probability:

Low - unlikely to happen

Medium - may happen

High - likely to happen

#### Risk Exposure = Impact * Probability

#### Risk Mitigation Strategy

Major (Rank of 6 or 9)		- Mitigate

Moderate (Rank of 3 or 4)		- Review

Minor (Rank of 1 or 2)		- Accept

# RISK REVIEW SCHEDULE

The initial risk management plan draft will be completed May, 2001 and will be presented to the project's Executive Oversight Committee (EOC) at the ____________, 2001 meeting, for approval.

The status of the actions for the risks selected to be mitigated will be reviewed by the EOC on a monthly basis during their regular status meeting.

The risk management process will be conducted, at a minimum, at the following times during the project:

- Quarterly beginning ___________________, 2001 through the end of the project

- At the completion of each major development phase (as specified in the work plan)

# RISK TRACKING and CONTROL

The tracking of risk mitigation actions will be done via the project work plan during the status reporting at the project steering committee meetings.

The control of the risk plan will be managed by including the triggers for invoking specific contingency actions in the work plan.  Additionally, the risk management process will be performed as defined by the above schedule.

SKIES IMPLEMENTATION PROJECT

RISK ASSESSMENT WORKSHOP

FEBRUARY 26, 2001

APPENDIX A

| Project Risks | Business Risks | Constraints | Environment | Technical | Implementation |
| --- | --- | --- | --- | --- | --- |
| Inadequate top management, sponsorship and support Lack of internal stakeholders’ commitments Limited large-scale project experience Inadequate change process Inadequate testing process Internal or external priority competition Scope management | Business disruption Compliance violations Agency credibility Market loss Lost opportunity costs Organizational demoralization Political discord | Resources Schedule Staff (tech. And business) Budget Facilities Contract Restrictions Dependencies Program Interfaces Customer Partners Contractors Management | Development Process Development System Management Process Planning Project organization Management experience Management Methods Monitoring Personnel management Quality assurance Configuration Management Work Environment Quality attitude Cooperation Communication Morale | Requirements Stability Completeness Clarity Validity Feasibility Precedent Scale Design Functionality Difficulty Interfaces Performance Testability Hardware Capability Non- developmental software capability Code and Unit Test System Integration Test Environment Product System User Acceptance Test Environment Product System | Schedule Business disruption Coordination |

| Project Risks | Business Risks | Constraints | Environment | Technical | Implementation |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Pilot Test Environment Product System Engineering Specialties Maintainability Reliability Safety Security Human factors Specifications |  |

SKIES IMPLEMENTATION PROJECT

RISK TRACKING WORKSHEET

APPENDIX B

| Risk # | Risk (Condition; Consequence) | Risk Category | Responsible | Impact | Prob. | Exposure (Rank) | Timeframe | Mitigation Strategy | Cost to Mitigate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |

SKIES IMPLEMENTATION PROJECT

RISK ACTION STATUS REPORT

APPENDIX D

| Risk # | Risk (Condition; Consequence) | Exposure (Rank) | Status | Assigned To | Due Date |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |